## Sample Bug Reports
Sample Bug Reports - Finance Banking Application (Reference Examples)
Secure Bank ¦ Manual QA Test Artifacts
Bug ID | Title / Summary | Module | Description | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Status | Environment | Build/Version | Reported By | Date Reported | Assigned To | Attachments/Screenshot | Comments
BUG_001 | Login fails with valid credentials on Chrome | Login | Login attempt with correct Customer ID and password does not succeed on Chrome browser | 1. Open app in Chrome v125 2. Enter valid Customer ID and Password 3. Click Login | User should be logged in and redirected to Dashboard | Error 'Invalid credentials' shown even though credentials are correct | Critical | High | Fixed | Chrome 125 / Windows 11 | Build 3.2.1 | Aman Naurangabadi | 20-Jul-2026 | Dev Team - Backend | screenshot_001.png | Reproducible on Chrome only; works fine on Firefox
BUG_002 | Fund transfer allows negative amount via API bypass | Fund Transfer | Entering a negative amount directly via request manipulation is accepted by backend | 1. Intercept transfer request 2. Modify amount to -500 3. Resend request | Backend should reject negative amount with validation error | Backend processes the transfer and debits are inconsistent | Critical | High | Open | Postman / Staging API | Build 3.2.1 | Aman Naurangabadi | 19-Jul-2026 | Dev Team - Backend | postman_log_002.png | Security/validation gap - server-side check missing
BUG_003 | MPIN change screen: Confirm MPIN field not masked | Account Mgmt | Confirm MPIN input field shows entered digits in plain text instead of masked dots | 1. Navigate to Change MPIN 2. Enter value in Confirm MPIN field | Field should mask entered digits like the New MPIN field | Digits are visible in plain text | Minor | Medium | Retest | Android App v2.4 / Pixel 7 | Build 3.2.1 | Aman Naurangabadi | 18-Jul-2026 | Dev Team - Mobile | screenshot_003.png | Fix deployed in build 3.2.2, pending verification
BUG_004 | Mini statement shows incorrect running balance after IMPS transfer | Fund Transfer | After a successful IMPS transfer, the mini statement briefly shows an incorrect running balance until refresh | 1. Complete an IMPS transfer 2. Immediately open Mini Statement without refreshing | Running balance should reflect the latest transaction instantly | Balance shown is stale for a few seconds | Major | Medium | New | iOS App v2.4 / iPhone 14 | Build 3.2.1 | Aman Naurangabadi | 17-Jul-2026 | Dev Team - Mobile | screenshot_004.png | Possible caching issue on client side
BUG_005 | Bill payment 'Auto-Pay' toggle resets after page refresh | Bill Payment | Auto-Pay toggle for an electricity biller appears OFF after refreshing the page, even though it was saved as ON | 1. Enable Auto-Pay for a biller and save 2. Refresh the page 3. Observe toggle state | Toggle should persist as ON after refresh, reflecting saved state | Toggle resets to OFF visually, though backend record is correct | Minor | Low | Open | Chrome 125 / Windows 11 | Build 3.2.1 | Aman Naurangabadi | 16-Jul-2026 | Dev Team - Frontend | screenshot_005.png | UI state sync issue, backend data unaffected